## Sheet1
CLASS 3300-004 |  |  | Notes: "Flags resolved" column not included. - Submission issues included in comments. - Bugs or issues in submissions moved to future iterations Requirements
Intro to Software Engineering
TEAM: | Shattered Protocols
REQ Lead: | T Fox
DATE: | 10/28/2024 (Initially defined in Github Projects 9/26)
Project Final Presentation - Requirements Spreadsheet
|  | CONFIGURATION MANAGEMENT |  |  |  |  | TEST |  |  |  | Final DELIVERY Date | Comments
|  | Team Member |  | Delivery Goal | Date Delivered | Days Late | Test Method | Team Member | Date Tested
ID | REQUIREMENT |  | INC/Ver | [6 empty] | # Flags
Template |  | T Write | Increment |  | Late by one day color cell yellow |  | T,A, I, O |  |  | # of issues
|  |  | version |  | Late by one week color cell red |  | T = test A=Analysis I=Inspection O=Observation
0 | Midterm Presentation | Team | Class | 2024-10-01 | 2024-09-29 | -2 | NA
1 | Presentation | Team | Class | 2024-12-12 |  | 0 | O,I
2 | Requirements Spreadsheet Submission | T Fox | Class | 2024-12-12 |  | 0 | O,I
3 | Dev Documentation | J Hong / T Fox | Class | 2024-12-12 |  | 0 | O,I
4 | User Documentation | S Welton | Class | 2024-12-12 |  | 0 | O,I
5 | Test Plan Documentation Submission | S Welton | Class | 2024-12-12 |  | 0 | O,I
6 | Test Reports Submission | S Welton | Class | 2024-12-12 |  | 0 | O,I
7 | Artifacts Delivery Document Submission | T Fox | Class | 2024-12-12 |  | 0 | O,I
8 | License Documentation and selection | J Hong | Class | 2024-12-12 |  | 0 | O,I
9 | Executable Submission | <Unassigned> | Class | 2024-12-12 |  | 0 | O,I
10 | ReadMe Submission | <Unassigned> | Class | 2024-12-12 |  | 0 | O,I
11 | Code Submission | <Unassigned> | Class | 2024-12-12 |  | 0 | O,I
12 | Project Idea Agreement | Team | Class | 2024-09-24 | 2024-09-24 | 0 | NA
13 | Must Have a Throughline Story Providing the player with context and goal | S Welton | Core | 2024-12-12 |  | 0 | A, I
14 | Must have imaginative and clear writing for player to easily visualize and navigate the world | S Welton | Core | 2024-12-12 |  | 0 | A,I
15 | Must have textbox input for keyword entry | T Fox | Core | 2024-12-12 |  | 0 | T,I
16 | Must have intuitive keyword player inputs | T Fox | Core | 2024-12-12 |  | 0 | T, A, I
17 | Must use reliable keywords (synonyms if possible) | T Fox | Core | 2024-12-12 |  | 0 | T,A,I
18 | Must allow player to check available commands at any time | T Fox | Core | 2024-12-12 |  | 0 | T,O
19 | Must implement several different logic pizzles of varying difficulty | J Hong | Core | 2024-12-12 |  | 0 | T,A,I,O
0 | Iteration Completion | Team | 0 | 2024-10-08 | 2024-10-22 | 14 | [5 empty] | Communication, organizational and scheduling issues prevented earlier completion of the iteration. Many parts were completed fairly early, but team conflicts prevented Iteration from properly resolving.
1 | Setup Main user input keyword structure | T Fox | 0 | 2024-10-08 | 2024-09-18 | -20 | A,I |  |  |  |  | Note: Original requirement and submission date were for the base objects setup, with intent to refine in future iterations. Submission of polished components was 10/18 technically 7 days past target due date. The objects were refined significantly during this time period, but not submitted to team Git due to team conflict and organizational concerns, and considering leaving the team.
2 | Setup Player Object | T Fox | 0 | 2024-10-08 | 2024-09-18 | -20 | A,I
3 | Setup Keyword Input Model | T Fox | 0 | 2024-10-08 | 2024-09-18 | -20 | A,I
4 | Setup Game Object | T Fox | 0 | 2024-10-08 | 2024-09-18 | -20 | A,I
5 | Setup Room Object | T Fox | 0 | 2024-10-08 | 2024-09-18 | -20 | A,I
6 | Make Map Object* | T Fox | 0 | 2024-10-08 | 2024-10-18 | 10 | A,I |  |  |  |  | Technically Added late to iteration as a better way of having rooms. Was part of a section of Git commits that I had not published due to team conflict issues (Uncertain if i was remaining with the team). So Actual completion date unknown
7 | Come up with Puzzle concepts* | J Hong | 0 | 2024-10-08 | 2024-09-29 | -9 | A |  |  |  |  | Came up with 1 concept only, and very bare bones concept. Requirement should have been better defined.
8 | Make General Story intro and concepts | S Welton | 0 | 2024-10-08 | 2024-09-29 | -9 | A |  |  |  |  | Defined in midterm presentation, actual submission may have been a day or two earlier
9 | Setup Puzzle Object Framework | J Hong | 0 | 2024-10-08 | 2024-09-29 | -9 | A,I |  |  |  |  | Completed by T Fox
10 | Set Prototype Script | S Welton | 0 | 2024-10-08 | 2024-09-27 | -11 | A,I |  |  |  |  | Defined in midterm presentation, actual submission may have been a day or two earlier
11 | Make Prototype Map Layout | S Welton | 0 | 2024-10-08 | 2024-09-27 | -11 | A,I |  |  |  |  | Defined in midterm presentation, actual submission may have been a day or two earlier
100 | Iteration 1 Completion (Initial Goal) | Team | 1 | 2024-10-14 | Cancelled | [6 empty] | Initial Iteration due date moved from 10/15/24 to 10/31/24 to reorganize. Due to Iteration 0 team conflicts.
100 | Iteration 1 Completion (Adjusted Goal) | Team | 1 | 2024-10-31 |  | 0
101 | Test Plan Documentation Creation | S Welton | 1 | 2024-11-04 | 2024-11-04 | 0 | O,I
102 | Requirements Spreadsheet Start | T Fox | 1 | 2024-12-12 | 2024-10-28 | -45 | O,I
103 | Make level 1 dungeon layout | S Welton | 1 | 2024-10-31 | 2024-09-27 | -34 | A,I |  |  |  |  | Prototype Layout continuing to be used for level 1
104 | First 6 Puzzles Designed and programmed | J Hong | 1 | 2024-10-31 | 2024-10-27 | -4 | A,I
105 | Track User Input to File | T Fox | 1 | 2024-10-31 | 2024-10-30 | -1 | T, I,O
106 | Update Room Name and Descriptions (So not all same) | S Welton | 1 | 2024-11-04 |  | 0 | A
IT-1.07 | Iteration 1.0 Test Report | S Welton | 1 | 2024-11-04 | 2024-11-04 | 0 | T,A,I,O
200 | Iteration 2 Completion | Team | 2 | 2024-11-05 |  | 0
200 | Decouple objects into event system | T Fox | 2 | 2024-11-18 |  | 0 | A,I
201 | Setup Programmatic Testing | J Hong | 2 | 2024-11-18 |  | 0 | A,I
202 | Improve Comments on Puzzle Classes | J Hong | 2 | 2024-11-18 |  | 0 | A,I
203 | Improve Comments on Core Classes | T Fox | 2 | 2024-11-18 |  | 0 | A,I
204 | Add to the puzzle description reason puzzle is being solved | S Welton | 2 | 2024-11-18 |  | 0 | A,I |  |  |  | 0
Formulas:
Delivery Goal = IF([REQUIREMENT]="","",IF([INC/Ver]=D54,E54,E54+14))
Delivery Goal = IF([REQUIREMENT]="","",IF([INC/Ver]=[INC/Ver, row above],[Delivery Goal, row above],[Delivery Goal, row above]+14))
Final DELIVERY Date = IF([REQUIREMENT]="","",IF([INC/Ver]=[INC/Ver, row above],[Final DELIVERY Date, row above],IF([Date Delivered]>0,[Date Delivered],"Not Delivered")))