## Sheet1
CLASS 3300-004 |  |  | Notes: "Flags resolved" column not included. - Submission issues included in comments. - Bugs or issues in submissions moved to future iterations Requirements
Intro to Software Engineering
TEAM: | Shattered Protocols
REQ Lead: | T Fox
DATE: | 10/28/2024 (Initially defined in Github Projects 9/26)
Project Final Presentation - Requirements Spreadsheet
|  | CONFIGURATION MANAGEMENT |  |  |  |  | TEST |  |  |  | Comments
|  | Team Member |  | Delivery Goal | Date Delivered | Days Late | Test Method | Team Member | Date Tested
ID | REQUIREMENT |  | INC/Ver | [6 empty] | # Flags
Template |  | T Write | Increment |  | Late by one day color cell yellow |  | T,A, I, O |  |  | # of issues
|  |  | version |  | Late by one week color cell red |  | T = test A=Analysis I=Inspection O=Observation
0 | Midterm Presentation | Team | Class | 2024-10-01 | 2024-09-29 | -2 | NA
1 | Final Presentation | Team | Class | 2024-12-02 |  | 0 | O,I
2 | Requirements Spreadsheet Submission | T Fox | Class | 2024-12-02 |  | 0 | O,I
3 | Dev Documentation | J Hong / T Fox | Class | 2024-12-02 |  | 0 | O,I
4 | User Documentation | S Welton | Class | 2024-12-02 |  | 0 | O,I
5 | Test Plan Documentation Submission | S Welton | Class | 2024-12-02 |  | 0 | O,I
6 | Test Reports Submission | S Welton | Class | 2024-12-02 |  | 0 | O,I
7 | Artifacts Delivery Document Submission | Team | Class | 2024-12-02 |  | 0 | O,I
8 | License Documentation and selection | J Hong | Class | 2024-12-02 |  | 0 | O,I
9 | ReadMe | J Hong | Class | 2024-12-02 |  | 0 | O,I
10 | Code and Executable Submission | <Unassigned> | Class | 2024-12-02 |  | 0 | O,I
11 | Project Idea Agreement | Team | Class | 2024-09-24 | 2024-09-24 | 0 | NA
12 | Must Have a Throughline Story Providing the player with context and goal | S Welton | Core | 2024-12-02 | 2024-11-13 | -19 | A, I
13 | Must have imaginative and clear writing for player to easily visualize and navigate the world | S Welton | Core | 2024-12-02 |  | 0 | A,I
14 | Must have textbox input for keyword entry | T Fox | Core | 2024-12-02 |  | 0 | T,I
15 | Must have intuitive keyword player inputs | T Fox | Core | 2024-12-02 |  | 0 | T, A, I
16 | Must use reliable keywords (synonyms if possible) | T Fox | Core | 2024-12-02 |  | 0 | T,A,I
17 | Must allow player to check available commands at any time | T Fox | Core | 2024-12-02 |  | 0 | T,O
18 | Must implement several different logic pizzles of varying difficulty | J Hong | Core | 2024-12-02 |  | 0 | T,A,I,O
0 | Iteration Completion | Team | 0 | 2024-10-08 | 2024-10-22 | 14 |  |  |  |  | Communication, organizational and scheduling issues prevented earlier completion of the iteration. Many parts were completed fairly early, but team conflicts prevented Iteration from properly resolving.
1 | Setup Main user input keyword structure | T Fox | 0 | 2024-10-08 | 2024-09-18 | -20 | A,I |  |  |  | Note: Original requirement and submission date were for the base objects setup, with intent to refine in future iterations. Submission of polished components was 10/18 technically 7 days past target due date. The objects were refined significantly during this time period, but not submitted to team Git due to team conflict and organizational concerns, and considering leaving the team.
2 | Setup Player Object | T Fox | 0 | 2024-10-08 | 2024-09-18 | -20 | A,I
3 | Setup Keyword Input Model | T Fox | 0 | 2024-10-08 | 2024-09-18 | -20 | A,I
4 | Setup Game Object | T Fox | 0 | 2024-10-08 | 2024-09-18 | -20 | A,I
5 | Setup Room Object | T Fox | 0 | 2024-10-08 | 2024-09-18 | -20 | A,I
6 | Make Map Object* | T Fox | 0 | 2024-10-08 | 2024-10-18 | 10 | A,I |  |  |  | Technically Added late to iteration as a better way of having rooms. Was part of a section of Git commits that I had not published due to team conflict issues (Uncertain if i was remaining with the team). So Actual completion date unknown
7 | Come up with Puzzle concepts* | J Hong | 0 | 2024-10-08 | 2024-09-29 | -9 | A |  |  |  | Came up with 1 concept only, and very bare bones concept. Requirement should have been better defined.
8 | Make General Story intro and concepts | S Welton | 0 | 2024-10-08 | 2024-09-29 | -9 | A |  |  |  | Defined in midterm presentation, actual submission may have been a day or two earlier
9 | Setup Puzzle Object Framework | J Hong | 0 | 2024-10-08 | 2024-09-29 | -9 | A,I |  |  |  | Completed by T Fox
10 | Set Prototype Script | S Welton | 0 | 2024-10-08 | 2024-09-27 | -11 | A,I |  |  |  | Defined in midterm presentation, actual submission may have been a day or two earlier
11 | Make Prototype Map Layout | S Welton | 0 | 2024-10-08 | 2024-09-27 | -11 | A,I |  |  |  | Defined in midterm presentation, actual submission may have been a day or two earlier
100 | Iteration 1 Completion (Initial Goal) | Team | 1 | 2024-10-14 | Cancelled | [5 empty] | Initial Iteration due date moved from 10/15/24 to 10/31/24 to reorganize. Due to Iteration 0 team conflicts.
100 | Iteration 1 Completion (Adjusted Goal) | Team | 1 | 2024-10-31 |  | 0
101 | Test Plan Documentation Creation | S Welton | 1 | 2024-11-04 | 2024-11-04 | 0 | O,I
102 | Requirements Spreadsheet Start | T Fox | 1 | 2024-12-12 | 2024-10-28 | -45 | O,I
103 | Make level 1 dungeon layout | S Welton | 1 | 2024-10-31 | 2024-09-27 | -34 | A,I |  |  |  | Prototype Layout continuing to be used for level 1
104 | First 6 Puzzles Designed and programmed | J Hong | 1 | 2024-10-31 | 2024-10-27 | -4 | A,I
105 | Track User Input to File | T Fox | 1 | 2024-10-31 | 2024-10-30 | -1 | T, I,O
106 | Update Room Name and Descriptions (So not all same) | S Welton | 1 | 2024-11-04 | 2024-11-04 | 0 | A
IT-1.07 | Iteration 1.0 Test Report | S Welton | 1 | 2024-11-04 | 2024-11-04 | 0 | T,A,I,O
110 | Iteration 1.1 Test Report | S Welton | 1.1 | 2024-11-07 | 2024-11-04 | -3 |  |  |  |  | There was a slight delay with testing caused by GIT management issues on Dev side. Puzzle and Dev branches not properly merged, Taylor had to fix and re-push Sunday (11/3)
200 | Iteration 2 Completion | Team | 2 | 2024-11-12 |  | 0
200 | Decouple objects into event system | T Fox | 2 | 2024-11-10 | 2024-11-11 | 1 | A,I
202 | Improve Comments on Puzzle Classes | J Hong | 2 | 2024-11-10 | 2024-11-14 | 4 | A,I
203 | Improve Comments on Core Classes | T Fox | 2 | Delayed |  |  | A,I |  |  |  | I ended up having to do a LOT of code this iteration, so pushing this off for future iteration
204 | Add to the puzzle description reason puzzle is being solved | S Welton | 2 | 2024-11-10 | 2024-11-13 | 3 | A,I
207 | Map handles Room Generation not Individual Rooms (To prevent duplicate rooms issues) | T Fox | 2 | 2024-11-10 | 2024-11-09 | -1
208 | key item ends game properly | T Fox | 2 | 2024-11-10 | 2024-11-11 | 1
201 | Setup Programmatic Testing | J Hong | 2 | Cancelled |  |  | A,I |  |  |  | Seth and Juhan decided at the last minute that we just wont do automated testing.
209 | Generate Gameplay Test File | S Welton / J Hong | 2 | Cancelled | [6 empty] | Seth and Juhan decided at the last minute that we just wont do automated testing.
205 | *(If time) Break Puzzles into Clue Items so passwords arent provided with puzzle | J Hong | 2 | Cancelled
206 | Doors locking.unliocking | T Fox | 2 | Delayed | [6 empty] | Implemented base logic, but still need to finish Events that actually handle the locking/unlocking
210 | Add Reset Counter to Start() methods for puzzles | J Hong | 2 | 2024-11-10 | 2024-11-07 | -3
207 | Start Dev Document | J Hong | 2 | 2024-11-10 | 2024-11-11 | 1
208 | License Documentation and selection | J Hong | 2 | 2024-11-10 | 2024-11-11 | 1
209 | Intro/Outro Text Display | S Welton | 2 | 2024-11-10 | 2024-11-13 | 3
209 | Iteration 2 Test Report | S Welton | 2 | 2024-11-11 | 2024-11-15 | 4 |  |  |  |  | There was a slight delay with testing caused by GIT management issues on Dev side. Puzzle and Dev branches not properly merged, Taylor had to fix and re-push Sunday (11/3)
300 | Iteration 3 Completion | Team | 3 | 2024-11-12 |  | 0
301 | Make Puzzle Nullable without breaking game (Room line 88) | T Fox | 3 | 2024-11-17 | 2024-11-16 | -1
302 | Finish Door Locking/Unlocking | T Fox | 3 | 2024-11-17 | 2024-11-16 | -1
303 | Fix Puzzle being run when re-entering room after already being solved | T Fox | 3 | 2024-11-17 | 2024-11-14 | -3
304 | Final room you must enter keycard to get the final puzzle | T Fox | 3 | 2024-11-17 | 2024-11-16 | -1
305 | *If time, make room puzzles show when attempting to use a locked door or something | T Fox | 3 | 2024-11-17 | 2024-11-10 | -7 |  |  |  |  | This was already happening last iteration, dont know why i thought it wasnt.
306 | *if time have the game SHOW that doors are locked on entry | T Fox | 3 | 2024-11-17 |  | 0
307 | Add additional Comments to Core Programming parts | T Fox | 3 | 2024-11-17 |  | 0
308 | *if time add "Inspect" functionality to items | T Fox | 3 | 2024-11-17 |  | 0
309 | Rework Hash puzzle | J Hong | 3 | 2024-11-17 |  | 0
310 | Save/Load system with Serializable objects/ JSONUtility | J Hong | 3 | 2024-11-17 |  | 0
311 | User Documentation | S Welton | 3 | 2024-11-17 |  | 0 |  |  |  |  | There was a slight delay with testing caused by GIT management issues on Dev side. Puzzle and Dev branches not properly merged, Taylor had to fix and re-push Sunday (11/3)
312 | Update Readme | J Hong | 3 | 2024-11-17 |  | 0
313 | More formatting so the game isnt just a gross wall of text | S Welton | 3 | 2024-11-17 |  | 0
314 | Test making Executable (How hard is it?) | T Fox | 3 | 2024-11-17 |  | 0
315 | *if time: Computer console setup for accessing puzzles rather than automatic |  | 3 | 2024-11-17 |  | 0
316 | Breakroom: If R2 door is unlocked use R4 puzzle, and the opposite. | J Hong | 3 | ` |  | 0
317 | Add new Puzzle for Breakroom | J Hong | 3 | 2024-11-18
318 | Add additional comments to Puzzle comments | J Hong | 3 | 2024-11-19 |  | 0
319 | Iteration 3 plan report | S Welton | 3 | ` |  | 0
320 | Iteration 3 Test Report | S Welton | 3 | 2024-11-18 |  | 0
Formulas:
Delivery Goal = IF([REQUIREMENT]="","",IF([INC/Ver]=D61,E61,E61+14))
Delivery Goal = IF([REQUIREMENT]="","",IF([INC/Ver]=[INC/Ver, row above],[Delivery Goal, row above],[Delivery Goal, row above]+14))